## Slide 1: Assessment Study UAEU
Lamprini Lambropoulou | European Commission - DG REGIO
Coordinators’ & Action Leaders’ Meeting

## Slide 2: Key strengths & achievements (I)
Multi-level, multi-stakeholder approach is main added value of the UAEU: Fostered significant collaboration between cities, the Commission, Member States, other EU institutions, and other stakeholders
Provided unique opportunity for cities and other stakeholders to enter into dialogue, exchange views and ideas, find common ground, and instigate actions to address identified issues
Thematic Partnership approach enabled to identify specific bottlenecks for cities and to develop concrete action plans to address these. Pillars and themes were considered very relevant
Flexible, ‘experimental’ nature of TPs was a key enabler: allowed TPs to take a genuinely ‘bottom-up’ approach and define their own remit, focus and working methods

## Slide 3: Key strengths & achievements (II)
Action Plans are beginning to generate tangible impacts:
  reportedly influenced a few Commission legislative proposals
  Guidelines/recommendations to improve implementation of existing legislation
  large number of best practices, guides, toolkits and roadmaps
Certain, albeit limited influence in strengthening the urban dimension in policy design and implementation at EU and national level; new national structures inspired by the UAEU
UAEU is increasingly the “common frame” for urban policies at EU level, with other EU programmes, policies and initiatives being aligned to the UAEU’s topics

## Slide 4: Weaknesses & issues to address (I)
Implementation of actions is often uncertain: There are serious doubts about the extent to which TP members (or other stakeholders) are able to fully implement their action plans
Relatively few actions focus on Better Regulation or Better Funding: Prevalence of Better Knowledge actions raises questions about TPs’ level of ambition and ultimate impacts
Lack of clear and transparent processes, requirements and specific objectives: Led among others to uncertainties regarding the aims, content and implementation of actions

## Slide 5: Weaknesses & issues to address (II)
Level of engagement of stakeholders in and with UAEU was uneven: Progress relied heavily on ‘hard core’ of engaged TP members, especially coordinators. MS and some DGs less involved
Limited outreach to stakeholders who are not directly involved in UAEU: Some TPs reached out to a “second circle” of cities, but overall the profile and visibility of the UAEU remains quite low
Resource constraints were a challenge for TPs: Caused by the relatively small amounts available, and, in some cases, a lack of awareness on available funding

## Slide 6: Weaknesses & issues to address (III)
Governance mechanism for UAEU is not effective: The UDG and DGUM were only able to provide a limited extent of guidance and steer
Internal communication within and between different elements of the UAEU has been lacking: The flow of information between key actors (the Commission, TP coordinators, Technical Secretariat and governance bodies) was suboptimal
The internal and external coherence of the UAEU is low: Applies to both the alignment with other elements of the UAEU (such as the “one-stop-shop”) and the alignment with other relevant EU initiatives

## Slide 7: Considerations for the future
Implementation uncertain
Relatively few actions on Better Regulation or Funding
Lack of clarity & transparency
Uneven engagement of stakeholders
Limited outreach to external stakeholders
Resource constraints a challenge for TPs
Governance mechanism not effective
Internal communication was lacking
Low internal and external coherence
Enhancing the implementation and impact of actions
Improving the engagement of stakeholders in and with the UAEU
Refining UAEU governance mechanisms, internal comms, place in the wider policy framework
Key issues to be addressed

## Slide 8: Options to address key issues (I)
 | Option A: Continuation and deepening thematic approach | Option B: Shift towards holistic / integrated approach
1. Enhancing the implementation and impact of actions | Prolong current TPs with focus on implementing APs Stimulate amendments to current actions Formulate clear and transparent processes, requirements and specific objectives for TPs Promote cross-Partnership collaboration Improve information on the status of actions | End TPs in their current format Set up an alternative transversal / integrated working method, to allow former ‘core’ TP members to work together Systematic identification of lessons learned, challenges and solutions identified across TPs Identification and prioritisation of actions with potentially high impact and reasonable chance of implementation Joint proposal for implementation, combining and building on original actions

## Slide 9: Options to address key issues (II)
 | Option A: Continuation and deepening thematic approach | Option B: Shift towards holistic / integrated approach
2. Improving the engagement of stakeholders in and with the UAEU | Allow for a greater role of cities in the composition of TPs Ensure all TP members have sufficient relevant thematic expertise Ensure adequate resources for TPs Strengthen the relations of the TPs with relevant institutions Reach out to external actors not directly involved in TPs | Expand on the format of Coordinators meetings, e.g. via regular meetings of the core former TP members with high-level Commission and MS representatives Active engagement in thematic working groups Ensure adequate resources for engagement in holistic / integrated approach

## Slide 10: Options to address key issues (III)
 | Potential high-level changes and enhancements
3. Refining the UAEU’s governance mechanisms, internal communications, and place in the wider policy / institutional framework | Improved guidance from the DGUM/UDG and Commission for TPs, e.g. by more clearly defining roles of the DGUM, UDG and UATPG, and/or by ‘recalibrating’ the way the Commission coordinates and facilitates the UAEU Enhance the links between the UAEU and the decision making processes and policy cycles Enhancing the representation of cities in relevant decision-making / governance bodies at EU and national level Improve the alignment with Cohesion Policy programmes and other EU initiatives

## Slide 11
Study available here:
https://ec.europa.eu/regional_policy/en/newsroom/news/2020/01/15-01-2020-assessment-study-of-the-urban-agenda-for-the-european-union

## Slide 12: Thank you!